## LCC Master
LCC-Master-New-PL | [7 empty] | Severity Multipliers:
Lawson Change Control Master Listing - New P.L. | [7 empty] | A | B | C | D
All documentation is stored in \\ThisComputer\d$\Docs\LCC | [7 empty] | 2 | 1.5 | 1 | 0.5
[9 empty] | Databases | [5 empty] | Source Code | [9 empty] | Environment | [7 empty] | Planning and Tracking
LCC No. | Description | Lawson Env. | Level Apps | System Code | Original (source) program | Lawson Program Codes(s) | Changed Program Code(s) | Severity | Work File | Field Re-Use | Customized Lawson Table | New Custom Table | New Element | SQL Change | .scr | .rpt | PD | WS | User Exit | Kn, Skn | .sr | .or | New Program | .lib | New System Code | Menu | Help Text | Security | jobdef | Date In Production | Hours Calc | Criticality | Affected? | hide this column | Hours expected | Priority | Completed? | hide this column | Actual Hours
Weighting | [8 empty] | 0.5 | 0.5 | 1 | 1 | 0.25 | 1 | 0.5 | 0.5 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 1 | 1 | 1 | 1 | 1 | 1
LCC-001 | Cust Accrual Months | 7.2.4 | 8.0.2 | AR | AR10 | AR10 | AR10 | D | [6 empty] | X | [12 empty] | X |  | 2004-02-12 | 0.75 | 4 | X | 0.75 | 0.75 | 3 | X | 0.75 | 0.25
LCC-002 | New Company Property tracking screens | 8.0.3 | 8.0.2 | PA | n/a | ZP85, ZP86, ZP87, ZP88 |  | B |  |  |  | X |  |  | X |  | X | X |  |  |  |  | X |  |  | X |  |  |  |  | 4.125 | 2 | X | 4.125 | 4.125 | 2 |  | 0
LCC-003 | Put PO Number back on check stubs | 8.0.3 | 8.0.2 | AP | AP155 | AP155 | AP155 | D | [7 empty] | X | [13 empty] | 2004-03-09 | 0.25 | 1 | X | 0.25 | 0.25 | 1 | X | 0.25 | 0.33
LCC-004 | Customer Terms Maintenance | 8.0.3 | 8.0.2 | AR, TE | n/a | ZP01, ZP02 |  | B |  |  |  | X |  |  | X |  | X | X |  |  |  |  | X | [6 empty] | 2004-07-20 | 2.625 | 3 | X | 2.625 | 2.625 | 3 |  | 0
LCC-005 | PO Printing via LaserPrint NOW | 8.0.3 | 8.0.2 | PO | POI9, PO20 | POI9, PO20 | POI9, PO20 | D | [6 empty] | X | X | X | [12 empty] | 2004-06-30 | 1.5 | 1 | X | 1.5 | 1.5 | 1 | X | 1.5 | 0.75
LCC-006 | Clone PA52 to ZED7 | 8.0.3 | 8.0.2 | PA | PA52 | ZED7 |  | C | [6 empty] | X |  | X | X |  |  |  |  | X | [6 empty] | 2004-06-18 | 0.75 | 1 | X | 0.75 | 0.75 | 1 |  | 0
LCC-007 | Relabel HR11 fields | 8.0.3 | 8.0.2 | HR | HR11 | HR11 | HR11 | D | [6 empty] | X | [14 empty] | 2004-08-03 | 0.25 | 4 | X | 0.25 | 0.25 | 3 |  | 0
LCC-008 | Clone HR and PA programs | 8.0.3 | 8.0.2 | HR, PA | HR11 HR20 PA12 PA26 | ZR9X ZMBK ZHAX ZUZU |  | C | [6 empty] | X |  | X | X |  |  |  |  | X | [6 empty] | 2004-08-04 | 0.75 | 1 | X | 0.75 | 0.75 | 1 |  | 0
LCC-009 | Acquisition - Sales Class ID Methodology | 8.0.3 | 8.0.2 | [26 empty] | n/a | 0 | 3 |  | 0 | 0 | 3 |  | 0
LCC-010 | Clone training screens - Remove key numbers | 8.03 | 8.0.2 | HR | HR55, HR155, TR00-TR222 | ZR55, ZR155, ZR00-ZR222 |  | C | [6 empty] | X | X | X | X |  |  |  |  | X | [6 empty] | Retracted |  |  |  | 0 |  |  |  | 0
LCC-011 | Customer Profile/Reporting | 8.03 | 8.0.2 | AR / ZP | AR10 | ZP10 |  | B |  | X |  | X |  |  | X |  | X |  |  |  | X | X | X |  |  | X |  |  |  |  | 5.0625 | 2 | X | 5.0625 | 5.0625 | 2 |  | 0
LCC-012 | Improve Payroll History Load CSV | 8.0.3 | 8.0.2 | PR | PR560 | ZP560 |  | D | [6 empty] | X | X | X | X |  |  |  |  | X | [6 empty] | 2005-01-21 | 0.4375 | 2 | X | 0.4375 | 0.4375 | 2 |  | 0
LCC-013 | 2004 1099 update | 8.0.3 | 8.0.2 | AP | AP145 | AP145 |  | D | [6 empty] | X | [14 empty] | 2005-01-25 | 0.25 | 3 |  | 0 | 0 | 3 |  | 0
LCC-014 | Add UserID to Time Entry | 8.0.3 | 8.0.2 | PR | HS36 | HS36 | HS36 | D | [8 empty] | X | [12 empty] | 2005-01-27 | 1 | 1 | X | 1 | 1 | 1 |  | 0
LCC-015 | Custom Menus | 8.0.3 | 8.0.2 | all | N/A | "PH" menus |  | D | [17 empty] | X |  |  |  | early 1997 | 0.5 | 1 | X | 0.5 | 0.5 | 1 |  | 0
LCC-016 | Date-based PRPENDTIME extract | 8.0.3 | 8.0.2 | PR |  | ZP535 |  | B | X | [5 empty] | X | X | X | X |  |  |  |  | X |  |  | X |  |  |  | 2005-02-25 | 3.5625 | 2 |  | 0 | 0 | 2 |  | 0
LCC-016a | Add EMPCOMMENT extract | 8.0.3 | 8.0.2 | PR |  | ZP535 | ZP535 | B | X | [5 empty] | X | X | X | X |  |  |  |  | X | [7 empty] | 2.0625 | 2 | X | 2.0625 | 2.0625 | 2 | X | 2.0625 | 2
LCC-017 | Item Master Custom Delete | 8.0.3 | 8.0.2 | IC | IC11 | ZP11 |  | C | [8 empty] | X | X |  |  |  |  | X | [6 empty] | 2005-02-24 | 0.625 | 4 | X | 0.625 | 0.625 | 3 |  | 0
LCC-018 | Product Parameters | 8.0.3 | 8.0.2 | ZC |  | ZC01 - ZC07 |  | A |  |  |  | X |  |  | X |  | X | X |  | X | X |  | X |  |  | X |  |  |  | 2005-04-22 | 6 | 3 | X | 6 | 6 | 3 |  | 0
LCC-019 | Imaging Signing Authority |  |  | ZP |  | ZP20 |  | A |  |  |  | X |  |  | X |  | X | X | X |  | X |  | X |  |  | X |  |  |  | 2005-04-22 | 6 | 2 | X | 6 | 6 | 2 |  | 0
LCC-020 | New Purge program | 8.0.3 | 8.0.2 | HR |  | ZP601 |  | B | [6 empty] | X | X | X | X |  |  |  |  | X |  |  | X |  |  |  | 2005-04-12 | 2.8125 | 3 | X | 2.8125 | 2.8125 | 3 |  | 0
LCC-021 | Add Vendor # to Drill-Around | 8.0.3 | 8.0.2 | AP |  | AP.or | AP.or | D | [13 empty] | X | [7 empty] | 2005-04-29 | 0.25 | 2 | X | 0.25 | 0.25 | 2 |  | 0
LCC-022 | HR Data Drill-Around Security | 8.0.3 | 8.0.2 | HR |  |  |  | C | [20 empty] | X |  | 1 | 2 | X | 1 | 1 | 2 |  | 0
[31 empty] | 0 |  |  | 0 | 0 |  |  | 0
[31 empty] | 0 |  |  | 0 | 0 |  |  | 0
[31 empty] | 0 |  |  | 0 | 0 |  |  | 0
[31 empty] | 0 |  |  | 0 | 0 |  |  | 0
[31 empty] | 0 |  |  | 0 | 0 |  |  | 0
[30 empty] | TOTAL: | 40.5625 | hrs |  |  | 36.75 | hrs |  |  | 3.33 | hrs
[33 empty] | Percent Completed: | [5 empty] | 12.41%
[33 empty] | Hours Expected: | [5 empty] | 4.5625 | hrs
[33 empty] | Hours Variance: | [5 empty] | -1.2325 | hrs
[33 empty] | Percent Over/Under: | [5 empty] | -27.01%
Note on A7: Values are approximate. Adjust as experience dictates.
Note on B6: Brief description of change.
Note on E18: MTsukroff: New System Code keeps data, screens, rules isolated
Note on F6: Program which has been changed or copied. Lets you see the impact of CTP's and MSP's, updates, etc.
Note on H6: Program that has been modified
Note on I1: Severity Multipliers are used to adjust final hours calculation.
Note on I6: A - Major Change B - Minor change C - Major Tweak D - Minor Tweak
Note on M11: ZPCUSTERMS, ZPCSTRMLOG
Note on O6: Change to database entirely outside Lawson - Stored procedures, triggerts, etc.
Note on P12: Only PO20.scr modified
Note on Q12: Supplied by RR Donnelly (Moore Wallace) but patched by Mtsukroff at R1G5.
Note on R12: Patch supplied by MTsukroff
Note on S6: Working Storage
Note on U6: Key Number, System Key Number
Note on V6: Screen Rules file (Selects)
Note on W6: Object Rules file (Drill-Around)
Note on X6: New Program was created, either cloned or entirely new
Note on X7: This is a multiplier factor, reducing the amount of work needed when a new program is created.
Note on X11: TE: ZP01 AR: ZP02
Note on Y6: Library change
Note on AA6: Menu change or customization
Note on AC6: Security changes vary greatly in amount of work needed
Note on AE6: Date of final installation into production
Note on AE37: Grand Total for all LCC's
Note on AG6: Determine criticality by frequency and immediacy of use: 1 - Critical, used every day 2 - Frequently used 3 - Month/year end 4 - Infrequently used or cosmetic change only
Note on AH39: Calculated on predicted time, not actual time.
Note on AH41: Hours over or under Hours Expected
Note on AH42: Percentage over or under Hours Expected
Note on AK6: Use Criticality to help determine your Priority: Level 1: Cannot go live without LCC applied. Level 2: Can finish LCC after go-live Level 3: Does not seriously affect operation, can be done last